## Table
| S.No. | Task | Assigned to | Medium (Mail/To do list) | Assigned date | Days since task assignment | Status | Description, if any
| 1 | Push ops leaders for DC proximity projects; classify soft QNS vs NCP | Rupam Bindra | To do | 2025-12-01 | 1 | A | Meeting this week to decide soft QNS vs NCP
| 2 | Complete VOC analysis; confirm meeting date with Karan | Rupam Bindra | To do | 2025-12-01 | 1 | A | Follow Vivek's template for VOC update
| 3 | Continue Navan handover; monitor ISO audit for Hickory | Rupam Bindra | To do | 2025-12-01 | 1 | A | Internal handover from Vivek; audit started with Sunit
| 4 | Close NCS items and initiate roadshows | Rupam Bindra; Sudeepta Kumar | To do | 2025-12-01 | 1 | A | Roadshows to start this week
| 5 | AB testing of scripts; create QA form for hotel planner | Bimbo Gatchalian | To do | 2025-12-01 | 1 | A | Compare new vs current scripts; create complementary QA form
| 6 | Ensure HP account T&Q engagement during OJT | Ruth Gay Calupig; Rupam Bindra; Bo | To do | 2025-12-01 | 1 | A | Keep teams involved through initial stressful period; reward & acknowledge
| 7 | Finalize Guide AI IDs pricing with KC vendor and Parmeet | Digvijay Rathore | To do | 2025-11-01 | 31 | A | Latest quote $88 from KC; align with Parmeet
| 8 | Upload D-Site modules on WNS LMS; confirm costing & licenses with Anthony | Alan Dsilva | To do | 2025-12-01 | 1 | A | Start PKT sessions across sites
| 9 | Roll out Quality PKT across locations | Alan Dsilva | To do | 2025-12-01 | 1 | A | Calibrate note before sending; align with Ashish's request
| 10 | T+ walkthrough and calibration with Sunil, Ruth, Nandita, Sudeepta | Alan Dsilva | To do | 2025-12-01 | 1 | A | Consider batch run or alternative approach for WS-wide usage
| 11 | Conduct a TMC walkthrough for Quality Leaders | Ruth Gay Calupig | To do | 2025-12-01 | 1 | A | KT
| 12 | Release MoM of TQ update call(1st Dec) to Abhin via mail | Digvijay Rathore | To do | 2025-11-01 | 31 | G | Completed
Planner | 13 | Lead Projects submission on Brainwave | Pradnya Chandgude;Anup Kumar Patel;Sheetal Kontham;Anish Bhardwaj | Planner | 20/11/2025 | #VALUE! | R |  | Not started
| 14 | Projects from SA | Nadiem Fredericks, Alan Dsilva | Planner | 24/11/2025 | #VALUE! | R |  | Not started
| 15 | Stevie award submission | Sunil Joshi;Sushil Ranade;Sugandha Leekha;Nandita Yadav | Planner | 24/11/2025 | #VALUE! | G |  | Completed
| 16 | NCP update for CEO review | Rupam Bindra;Vivek Srivastava | Planner | 24/11/2025 | #VALUE! | R |  | Not started
| 17 | Fraud risk control assessment | Digvijay Rathore;Rupam Bindra;Vivek Srivastava | Planner | 21/11/2025 | #VALUE! | A | From Abhin: Identify all Fraud related risks across accounts. Check for client acceptance to these risks and where does the liability lie From Digvijay: OC&H Fraud Risks: [https://app.powerbi.com/groups/me/reports/edca8a3c-beb1-4c21-9506-b70bb25f108e/ReportSectionb06a183992731327f25a?ctid=23f8ecfb-6a90-46c2-96ca-4a362721b82c&experience=power-bi](https://app.powerbi.com/groups/me/reports/edca8a3c-beb1-4c21-9506-b70bb25f108e/ReportSectionb06a183992731327f25a?ctid=23f8ecfb-6a90-46c2-96ca-4a362721b82c&amp;experience=power-bi) A&A Fraud Risks: [https://app.powerbi.com/groups/me/reports/edca8a3c-beb1-4c21-9506-b70bb25f108e/ReportSectionb06a183992731327f25a?ctid=23f8ecfb-6a90-46c2-96ca-4a362721b82c&experience=power-bi](https://app.powerbi.com/groups/me/reports/edca8a3c-beb1-4c21-9506-b70bb25f108e/ReportSectionb06a183992731327f25a?ctid=23f8ecfb-6a90-46c2-96ca-4a362721b82c&amp;experience=power-bi) | In progress
| 18 | DSiTE Demo for SA E&U Team | Member;Digvijay Rathore | Planner | 20/11/2025 | #VALUE! | R |  | Not started
| 19 | Share the SLA slides from Utilities review completed at Blackriver office | Katja Alves;Nadiem Fredericks | Planner | 21/11/2025 | #VALUE! | R |  | Not started
| 20 | Share the SLA slides from Utilities review completed at Blackriver office | Katja Alves;Alan Dsilva;Nadiem Fredericks | Planner | 24/11/2025 | #VALUE! | R |  | Not started
| 21 | Weekly update slide to include Training and Quality actions - Utilities | Katja Alves;Alan Dsilva;Digvijay Rathore;Nadiem Fredericks | Planner | 24/11/2025 | #VALUE! | A | This is the weekly SLA update slide (Friday meeting) shared by Nadiem with me. | In progress
| 22 | Monthly reports | Digvijay Rathore | Planner | 21/11/2025 | #VALUE! | R | - Agent Error report - Extra HC report - Speed to bilability - Updated Attrition file - VOC, Health Scorecard, SLA Dashboard - | Not started
| 23 | Stevie award submission | Sunil Joshi;Sugandha Leekha;Nandita Yadav | Planner | 24/11/2025 | #VALUE! | G | closed | Completed
| 24 | Rupam / Abhin - 1x1 | Rupam Bindra | Planner | 21/11/2025 | #VALUE! | R | Points from call today.. Date: 30 Sept 2025 QA Automation FMEA → Review for all accts Money In / Money Out Process Maps Reward & Penalties → Threshold %age Fraud Risks → Contacts Urgently Audit QSD → Relevance, adequacy & version control Business Insight → Bo & Sushil → Rupam to inform me when she’s had that convo Account Health Scorecard Common Minimum Practices Feedback tone & Consistency specificity → Sushil Resolution Rate → VS Client Escalation KRA for everyone → + Tracking | Not started
| 25 | Quality team task assessments | Rupam Bindra;Vivek Srivastava | Planner | 21/11/2025 | #VALUE! | R | Assess following: Daily weekly monthly audit targets Accounts that use randomizer vs not.. how is the point related to cherry picking being validated Accounts where QA score is a SLA Check if QA score is part of QA or AM/DM/Manager incentives If ATA/CTC is done for each account.. who does it and what’s the variance If client calibrations are done regularly and what is the variance How to ensure that scores are not kept high or low artificially | Not started
| 26 | Annual performance update with BPR team | Pradnya Chandgude;Pritesh Saikia;Anup Kumar Patel;Sheetal Kontham;Anish Bhardwaj | Planner | 24/11/2025 | #VALUE! | R | Mail sent with details. | Not started
| 27 | Annual performance update with BPR team | Pradnya Chandgude;Pritesh Saikia;Anup Kumar Patel;Sheetal Kontham;Anish Bhardwaj | Planner | 25/11/2025 | #VALUE! | R | Mail sent with details. | Not started
| 28 | SLA report - weekly Andon chart | Digvijay Rathore | Planner | 21/11/2025 | #VALUE! | R |  | Not started
| 29 | KRA PBI report for NY span - Incl SA teams | Nandita Yadav | Planner | 21/11/2025 | #VALUE! | A | 1 Dev has been discussed and agreed as date for rollout for NY span. WIP . We are migrating old files to the new automated sheet . | In progress
| 30 | SLA report - weekly Andon chart | Digvijay Rathore | Planner | 25/11/2025 | #VALUE! | R |  | Not started
| 31 | NCP process and how it should be managed | Rupam Bindra;Vivek Srivastava | Planner | 25/11/2025 | #VALUE! | R | All NCP must be logged into BPET portal and Wns should be identified. If Finance approves, then its NCP else its QNS. | Not started
| 32 | Follow up actions from SA Team Meeting | Anup Kumar Patel;Katja Alves;Alan Dsilva;Ruth Gay Calupig;Nadiem Fredericks;Rupam Bindra;Nandita Yadav | Planner | 21/11/2025 | #VALUE! | R | Follow up actions from the T&Q meeting with SA Team . **D Site Demo and Deployment Ideas: **Organize a D Site demo for all team members (including quality function), and collect at least two unique deployment ideas per person to be logged into Brainwave. (Katja) . **D Site Deployment Tracking: **Track and publish a list of team members who have not submitted their D Site deployment ideas after the demo. (Katja) . **D Site Deployment in South Africa: **Work with Digvijay to deploy the D Site dashboard for South Africa accounts starting next month, coordinating with Nadeem, Allen (utilities), and Ruth (travel). (Digvijay, Nadeem, Allen, Ruth) . **Moment of Truth Project Teams: **Nominate 5 people for each of the identified projects (complaints, under compliance, collections, etc.), form groups of four for each, and ensure detailed process maps are created and logged as brainwaves within a week. (Nadeem, Aneesh) . **Moment of Truth Project Mentoring: **Mentor the nominated teams in creating detailed process flow diagrams for the identified projects and ensure all are logged as brainwaves or BI before end of tomorrow with clear leaders and team members. (Anish) . **Segmentation Analysis for Messaging Accounts: **Complete process flow diagrams (level 4) for all Centrica messaging LOBs in India where there are penalties, and report the number of brainwaves and LOBs by next week Friday. (Sandeep) | Not started
| 33 | Weekly tasks | Digvijay Rathore | Planner | 21/11/2025 | #VALUE! | R | Summary Snapshot of SLA Dashboard Transitions Dashboard Client meeting tracker - send a snapshot update, including reminders for packs Projects dashboard, how many added/completed People Analytics snapshot Escalation dashboard Weekly executive update from all items tracked | Not started
| 34 | Weekly tasks | Digvijay Rathore | Planner | 21/11/2025 | #VALUE! | A | - Summary Snapshot of 1. SLA Dashboard 2. Transitions Dashboard 3. Client meeting tracker - send a snapshot update, including reminders for packs 4. Projects dashboard, how many added/completed 5. People Analytics snapshot - | In progress
| 35 | TMC Academy launch | Ruth Gay Calupig;Nandita Yadav | Planner | 02/12/2025 | 293 | R |  | Not started
| 36 | Minutes of meeting - Fortnightly meet | Ruth Gay Calupig;Rupam Bindra;Nandita Yadav | Planner | 02/12/2025 | 293 | R |  | Not started
| 37 | Accountability dashboard | Digvijay Rathore | Planner | 02/12/2025 | 293 | R | Add all actions from this tracker and from mails allocated to all leaders and track those with RAG status. | Not started
| 38 | Daily call for Blockskye and Call for HP on Wednesday | Rupam Bindra | Planner | 28/11/2025 | #VALUE! | R |  | Not started
| 39 | Alan / Abhin - 1x1 | Alan Dsilva | Planner | 27/11/2025 | #VALUE! | R | - Creation of a Treasure portal for Training questions for RFP across the SBU. This should be made such that all Training Leaders are contributing to the portal and then teams can start using the responses for their future RFPs - Create and draft Treasure Portal structure - Ensure awareness across the leaders - Contribution to the portal to be done by all leaders - Governance of the same - Usage of the responses - Operations / Delivery Management: - Training MUST be part of ALL Operations Review, with leaders representing their respective functions - There MUST be a regular departmental review with me to ensure that ALL process progress and ALL Training Digitization initiatives, within Accounts / within BU / within SBU / within Company are being done.. - Monthly PKT to be conducted for ALL supervisors and you MUST take ownership of the governance regarding this 'Knowledge Process' for supervisors across the BU - To get FULLY aligned with NCP concepts - understand what is Non Contractual Productivity and how do you and Training function plays a role in this aspect of the business - Technology Enablement - - TAAS - Pipeline - Connect with Sunil and how that can be replicated across your business - Cold Calling - Detailed discussion around TAAS and how this is being pursued | Not started
| 40 | Incorrect QA marking in Centrica - Mail from Gareth, Shona and Shikha | Nadiem Fredericks | Planner | 27/11/2025 | #VALUE! | A |  | In progress
| 41 | Centrica guide ai and Dsite modules | Katja Alves;Alan Dsilva;Digvijay Rathore | Planner | 27/11/2025 | #VALUE! | A | What is the client mail on using Dsite and guide ai in Centrica? | In progress
| 42 | Excess / Deficit HC report | Digvijay Rathore | Planner | 27/11/2025 | #VALUE! | R | This is basi the mail sent by Nitesh. | Not started
| 43 | Risk review for OC&H - mail from Ashish Bhargava | Rupam Bindra | Planner | 27/11/2025 | #VALUE! | R |  | Not started
| 44 | Navan handover | Vivek Srivastava | Planner | 27/11/2025 | #VALUE! | R |  | Not started
| 45 | Centrica regular QA report - ownership and date | Digvijay Rathore;Nadiem Fredericks | Planner | 27/11/2025 | #VALUE! | R | This is for the Centrica daily quality reporting that I discussed with the team. Nadiem is to share that information today latest. | Not started
| 46 | Replacement options for Zenarate | Alan Dsilva;Digvijay Rathore | Planner | 27/11/2025 | #VALUE! | R | Zenarate is not working out due to delayed response. Alternate must be explored. | Not started
| 47 | Stevie award submission | Sunil Joshi;Sushil Ranade;Sugandha Leekha;Nandita Yadav | Planner | 27/11/2025 | #VALUE! | R |  | Not started
| 48 | Annual performance update with BPR team | Pradnya Chandgude;Pritesh Saikia;Anup Kumar Patel;Sheetal Kontham;Anish Bhardwaj | Planner | 28/11/2025 | #VALUE! | R | Mail sent with details. | Not started
| 49 | Annual performance update with BPR team | Pradnya Chandgude;Pritesh Saikia;Anup Kumar Patel;Sheetal Kontham;Anish Bhardwaj | Planner | 28/11/2025 | #VALUE! | R | Mail sent with details. | Not started
| 50 | Annual performance update with BPR team | Pradnya Chandgude;Pritesh Saikia;Anup Kumar Patel;Sheetal Kontham;Anish Bhardwaj | Planner | 28/11/2025 | #VALUE! | R | Mail sent with details. | Not started
| 51 | Annual performance update with BPR team | Pradnya Chandgude;Pritesh Saikia;Anup Kumar Patel;Sheetal Kontham;Anish Bhardwaj | Planner | 28/11/2025 | #VALUE! | R | Mail sent with details. | Not started
| 52 | Annual performance update with BPR team | Pradnya Chandgude;Pritesh Saikia;Anup Kumar Patel;Sheetal Kontham;Anish Bhardwaj | Planner | 28/11/2025 | #VALUE! | R | Mail sent with details. | Not started
| 53 | Follow up actions from SA Team Meeting | Anup Kumar Patel;Katja Alves;Alan Dsilva;Ruth Gay Calupig;Nadiem Fredericks;Rupam Bindra;Nandita Yadav | Planner | 27/11/2025 | #VALUE! | A | Follow up actions from the T&Q meeting with SA Team . **D Site Demo and Deployment Ideas: **Organize a D Site demo for all team members (including quality function), and collect at least two unique deployment ideas per person to be logged into Brainwave. (Katja) . **D Site Deployment Tracking: **Track and publish a list of team members who have not submitted their D Site deployment ideas after the demo. (Katja) . **D Site Deployment in South Africa: **Work with Digvijay to deploy the D Site dashboard for South Africa accounts starting next month, coordinating with Nadeem, Allen (utilities), and Ruth (travel). (Digvijay, Nadeem, Allen, Ruth) . **Moment of Truth Project Teams: **Nominate 5 people for each of the identified projects (complaints, under compliance, collections, etc.), form groups of four for each, and ensure detailed process maps are created and logged as brainwaves within a week. (Nadeem, Aneesh) . **Moment of Truth Project Mentoring: **Mentor the nominated teams in creating detailed process flow diagrams for the identified projects and ensure all are logged as brainwaves or BI before end of tomorrow with clear leaders and team members. (Anish) . **Segmentation Analysis for Messaging Accounts: **Complete process flow diagrams (level 4) for all Centrica messaging LOBs in India where there are penalties, and report the number of brainwaves and LOBs by next week Friday. (Sandeep) | In progress
Formulas:
Days since task assignment = DAYS(TODAY(),[Assigned date])

## Sheet2
I have to make leader wise accountability dashboard. It will showcase the status of tasks assigned and completed by the leaders. It will be based on simple excel attached here. Think deeply and tell me what should be the reporting view of this excel information, which drives more completion and competition when published to the leaders. We can either create a power BI or polished and well designed HTML page with graphs, visuals and leader board.
Filters for leader names
RAG status not changing